Cottonwood Creek Project

| Goals: enhanced resilience to drought, increased water storage capacity, habitat and rangeland restoration, possible beaver reintroduction, increased flow in Cottonwood Ck and Boulder RIver |  |  |  |
| --- | --- | --- | --- |
| Planning | Dec 2025-Mar 2026 | Planning | Determine availability of any grants/programs, learn the current process requirements |
|  |  | Implement | Conifer encroachment mitigation |
|  |  | Paperwork | Contact Kris Hugulet at the Conservation District for a permit to build BDAs in Cottonwood Ck |
|  | March 5, 2026 | Consultant | Site visit by Torry Ritter of the Montana Beaver Working Group |
|  | April 2026 | Regulatory | EA for streamlined beaver transplant program in Montana will be decided. The decision will determine this aspect of the project’s path forward. |
|  |  | Implement | Conifer encroachment mitigation |
| Implement & Maintain | May-June 2026 | Implement | Build 7-10 BDAs in project area |
|  |  | Paperwork/ Consultant | Gather/determine required criteria about current site for application for beaver transplant: slope, sediment, water depth, willow and other food adequacy, etc. per the Beaver White Paper |
|  |  | Implement | Conifer encroachment mitigation |
|  | Jul-Sep 2025 | Grant work | DNRC decision on conifer mitigation grant, budget/project determination (July) |
|  |  | Implement | Conifer encroachment mitigation |
|  |  | Monitor/ Maintain | Maintain BDAs and repair as needed, maintain conifer-clear areas Monitor changes to water flow toward better beaver habitat |
| - The work September 2026 onward will be determined by too many factors to list. At a minimum, the BDAs could result in some improvements without any move toward beaver restoration, in which case we monitor and maintain the BDAs. There is always conifer mitigation. - Any planning for beaver restoration prior to the March site visit and April EA decision is premature. |  |  |  |